## Sheet1
2022-09-09 |  |  |  | 2022-09-09
Task | Estimation | Due date |  | Task | Estimation | Status | Due date |  | BadNumberFormatException
New features in Java 8, |  |  |  | New features in Java 8, |  |  |  |  | Exceptions
Lambda expression | 2hrs | 2022-09-09 |  | Lambda expression | 2hrs | Completed | 2022-09-09 |  | Run deals program
Repeating Annotations | 30min | 2022-09-09 |  | Repeating Annotations | 30min | Completed | 2022-09-09 |  | Exercise on annotations
Type Annotations | 30min | 2022-09-09 |  | Type Annotations | 30min | Completed | 2022-09-09 |  | Lambda expressions more details
Improved type inference | 45mins | 2022-09-09 |  | Improved type inference | 45mins | Completed | 2022-09-09 |  | Git
Method parameter reflection | 45mins | 2022-09-09 |  | Method parameter reflection | 45mins | Completed | 2022-09-09 |  | Use case
Date-Time APIs | 1hr | 2022-10-09 |  | LinkedList practice | 1hr | Completed | 2022-10-09
LinkedList practice | 1hr | 2022-10-09 |  | ArrayList practice | 1hr | Completed | 2022-10-09 |  | Indexing
ArrayList practice | 1hr | 2022-10-09 |  | HashSet practice | 1hr | Completed | 2022-10-09 |  | Commit
HashSet practice | 1hr | 2022-10-09 |  | Stack & Heap | 2hrs | Completed | 2022-11-09 |  | Roll back
Stack & Heap | 2hrs | 2022-11-09 |  | Logging - Log4j/SL4j | 2hrs | Completed | 2022-11-09 |  | ACID | Oracle DB installation
Logging - Log4j/SL4j | 2hrs | 2022-11-09 | [6 empty] | REST | Integration
SOAP
Bean
2022-12-09 | [8 empty] | Bean scope
Task | Estimation | Due date |  | Task | Estimation | Status | Due date |  | DI
Learning, |  |  |  | Learning, |  |  |  |  | Spring vs Spring boot
JSP | 30min | 2022-09-12 |  | JSP | 30min | In progress | 2022-09-12
Servelet | 30min | 2022-09-12 |  | Servelet | 30min | In progress | 2022-09-12 |  | Bean scope
ER Diagram | 30min | 2022-09-12 |  | ER Diagram | 30min | Completed | 2022-09-12 |  | Qualifier
SOLID principles | 30min | 2022-09-12 |  | SOLID principles | 30min | Completed | 2022-09-12
Design ER diagram | 40min | 2022-09-12 |  | Design ER diagram | 40min | Completed | 2022-09-12
Back-end implementation | 5hrs | 2022-09-13 |  | Back-end implementation | 5hrs | In progress | 2022-09-13
Front-end design & Implementation | 1.5hr | 2022-09-13 |  | Front-end design & Implementation | 1.5hr | In progress | 2022-09-13
2022-09-13
|  |  |  | Task | Estimation | Status | Due date
Front-end design & Implementation
|  |  |  | Registration form | 1hr | Completed | 2022-09-13
|  |  |  | User details UI | 1hr | Not Started | 2022-09-14
|  |  |  | Edit user UI | 1hr | Not Started | 2022-09-14
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 2022-09-13
|  |  |  | Notification implementation | 1hr | In progress | 2022-09-13
|  |  |  | Retrieve user | 2hr | Not Started | 2022-09-14
|  |  |  | Edit and save details | 2hr | Not Started | 2022-09-14
2022-09-14
|  |  |  | Task | Estimation | Status | Due date
Front-end design & Implementation
|  |  |  | Registration form | 1hr | Completed | 2022-09-13
|  |  |  | User details UI | 1hr | In progress | 2022-09-14
|  |  |  | Edit user UI | 1hr | In progress | 2022-09-14
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 2022-09-13
|  |  |  | Notification implementation | 1hr | Completed | 2022-09-13
|  |  |  | Retrieve user | 2hr | In progress | 2022-09-14
|  |  |  | Edit and save details | 2hr | Not Started | 2022-09-14
2022-09-14
|  |  |  | Task | Estimation | Status | Due date
Front-end design & Implementation
|  |  |  | Registration form | 1hr | Completed | 2022-09-13
|  |  |  | User details UI | 1hr | Completed | 2022-09-14
|  |  |  | Edit user UI | 1hr | Completed | 2022-09-14
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 2022-09-13
|  |  |  | Notification implementation | 1hr | Completed | 2022-09-13
|  |  |  | Retrieve user | 2hr | In progress | 2022-09-14
|  |  |  | Edit and save details | 2hr | In progress | 2022-09-14
2022-09-15
|  |  |  | Task | Estimation | Status | Progress | Due date | Worked hours
Front-end design & Implementation
|  |  |  | Registration form | 1hr | Completed | 100% | 2022-09-13 | 1.5hr
|  |  |  | User details UI | 1hr | Completed | 100% | 2022-09-14 | 1hr
|  |  |  | Edit user UI | 1hr | Completed | 100% | 2022-09-14 | 1.5hr
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 100% | 2022-09-13 | 4.5hrs
|  |  |  | Retrieve user | 2hr | Completed | 100% | 2022-09-14 | 6hr
|  |  |  | Edit and save details | 2hr | In progress | 80% | 2022-09-14 | 2hr
|  |  |  | Planning on combining exam and results with the system | 30mins | Not started |  | 2022-09-15
|  |  |  | Modify ER diagram | 30mins | Completed | 100% | 2022-09-15 | 20mins
|  |  |  | Changes on code based on new ER | 45mins | Not started
2022-09-16
|  |  |  | Task | Estimation | Status | Progress | Due date | Worked hours
Front-end design & Implementation
|  |  |  | Registration form | 1hr | Completed | 100% | 2022-09-13 | 1.5hr
|  |  |  | User details UI | 1hr | Completed | 100% | 2022-09-14 | 1hr
|  |  |  | Edit user UI | 1hr | Completed | 100% | 2022-09-14 | 1.5hr
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 100% | 2022-09-13 | 4.5hrs
|  |  |  | Retrieve user | 2hr | Completed | 100% | 2022-09-14 | 6hr
|  |  |  | Edit and save details | 2hr | In progress | 90% | 2022-09-14 | 2hr
|  |  |  | Planning on combining exam and results with the system | 30mins | Not started |  | 2022-09-15
|  |  |  | Modify ER diagram | 30mins | Completed | 100% | 2022-09-15 | 20mins
|  |  |  | Changes on code based on new ER | 45mins | Not started |  | 2022-09-16
|  |  |  | Taxi booking Use cases & scenarios | 1hr | Completed | 100% | 2022-09-16 | 2hrs
|  |  |  | Taxi booking ER diagram | 1hr | Completed | 100% | 2022-09-16 | 1hr
|  |  |  | Delete function implementation | 2hr | Completed | 100% | 2022-09-16 | 3hr
2022-09-18
|  |  |  | Task | Estimation | Status | Progress | Due date | Worked hours
Front-end design & Implementation
|  |  |  | Student details UI | 1hr | Completed | 100% | 2022-09-14 | 1hr
|  |  |  | Add student UI | 1hr | Completed | 100% | 2022-09-14 | 1.5hrs
|  |  |  | New home UI | 30mins | Completed | 100% | 2022-09-18 | 1hr
|  |  |  | Exam UI | 40mins | Completed | 100% | 2022-09-18 | 30mins
|  |  |  | Add Exam UI | 40mins | Completed | 100% | 2022-09-19 | 40mins
Back-end implementation
|  |  |  | Register user | 3hrs | Completed | 100% | 2022-09-13 | 4.5hrs
|  |  |  | Retrieve user | 2hr | Completed | 100% | 2022-09-14 | 6hrs
|  |  |  | Edit and save details | 2hr | Completed | 100% | 2022-09-14 | 4.5hrs
|  |  |  | CRUD creation for exams | 6hrs | Completed | 100% | 2022-09-19 | 7.5hrs
|  |  |  | Delete function implementation for Student | 2hrs | Completed | 100% | 2022-09-16 | 3hrs
|  |  |  | Modify ERD | 30mins | Completed | 100% | 2022-09-15 | 20mins
|  |  |  | Taxi booking usecases and scenarios | 1hr | Completed | 100% | 2022-09-16 | 2hrs
|  |  |  | Taxi booking ERD | 1hr | Completed | 100% | 2022-09-16 | 1hr
|  |  |  | Planning on combining exam with the system | 30mins | Completed | 100% | 2022-09-16 | 15mins
|  |  |  | Combine Results with the system | 10hrs | Not Started |  | 2022-09-20
|  |  |  | Task | Estimation | Status | Due date | Worked hours
|  |  | Front-end design & Implementation | Students UI | 4hr | Completed | 2022-09-19 | 4hrs 40mins
|  |  |  | Exam UI | 2hr | Completed | 2022-09-20 | 1.5hrs
|  |  |  | Marks UI | 1.5hr | Completed | 2022-09-20 | 2.5hrs
|  |  | Back-end Implementation | CRUD creation for student | 9hrs | Completed | 2022-09-14 | 18.5hrs
|  |  |  | CRUD creation for exams | 6hrs | Completed | 2022-09-19 | 7.5hrs
|  |  |  | CRUD creation for Marks | 10hrs | In Progress 60% | 2022-09-20 | 8hrs

## Sheet2
Task | Estimation time | Due date | Task | Estimation time | Progress | Due date | Worked hours | BufferedReader
Learn the technique to insert records via excel sheet to database | 1.5 hrs | 2022-09-27 | Learn the technique to insert records via excel sheet to database | 1.5 hrs | Completed | 2022-09-27 | 1hr | FileReader
Writing program to save details in MySQL database | 4hrs | 2022-09-27 | Writing program to save details in MySQL database | 4hrs | Completed | 2022-09-27 | 4hrs | Find technique to make the thread wait until user input
Learn about creating JAR and Batch file | 1.5hrs | 2022-09-28 | Learn about creating JAR and Batch file | 1.5hrs | Completed | 2022-09-28 | 15mins | Select file window should be closed after selecting the file
Create JAR file | 30mins | 2022-09-28 | Create JAR file | 30mins | Completed | 2022-09-28 | 1hr | Edit select file window for proper display
Create batch file | 40mins | 2022-09-28 | Create batch file | 40mins | Completed | 2022-09-28 | 1hr | Display status of insertion
Learn to create WAR file | 45mins | 2022-09-28 | Learn to create WAR file | 45mins | Completed | 2022-09-28 | 10mins | find the use of batchsize
Create WAR file for School student registration application | 30mins | 2022-09-28 | Create WAR file for School student registration application | 30mins | Completed | 2022-09-28 | 5mins | SQL script
Learn to deploy WAR file in Tomcat server | 1hr | 2022-09-28 | Learn to deploy WAR file in Tomcat server | 1hr | Completed | 2022-09-28 | 15mins | SoapUI
Deploy created WAR file in Tomcat server | 1hr | 2022-09-28 | Deploy created WAR file in Tomcat server | 1hr | Completed | 2022-09-28 | 5mins | Gradle vs Maven
|  |  | Access deployed project from another pc | 30mins | Completed | 2022-09-28 | 20mins | Types of build tools
Maven Practice
|  |  | Task | Estimation time | Progress | Due date | Worked hours
|  |  | Create document for differences between Maven and Gradle | 2hrs | Completed | 2022-09-30 | 2.5hrs
Try Maven plugins,
|  |  | Maven Clean | 20mins | Completed | 2022-10-03 | 30mins
|  |  | Maven Test | 20mins | Completed | 2022-10-03 | 10mins | Lombok
|  |  | Maven Build | 20mins | Completed | 2022-10-03 | 30mns
|  |  | Maven Install | 20mins | Completed | 2022-10-03 | 15mins | curl command
Spring vs springboot
JPA - ORM
|  |  | Task | Estimation time | Progress | Due date | Worked hours
|  |  | Implementation of create, read operations for student management system using spring boot | 5hrs | Completed | 2022-10-04 | 5hrs
|  |  | Learn Spring vs Spring boot | 1hr | Not Started | 2022-10-05 | -
|  |  | Learn Dependency scopes | 1.5hrs | Not Started | 2022-10-05 | -
|  |  | Task | Estimation time | Progress | Due date | Worked hours
|  |  | Configure Swagger for student management system | 1hr | Completed | 2022-10-05 | 2hrs
|  |  | Learn and try logging | 2hrs | Completed | 2022-10-05 | 3.5hrs
|  |  | Try Oracle and PostgreSQL Databases for student management system | 2hrs | Completed | 2022-10-06 | 4.5hrs
|  |  | Create different application.properties files for student management system and run the system respectively for the files | 2hrs | Completed | 2022-10-06 | 1hr
|  |  | Task | Estimation time | Progress | Due date | Worked hours | StomClient
|  |  | Replace request mapping parameters by constants | 15mins | Completed | 2022-10-07 | 15mins | TCP
|  |  | Study about RestApi best practices | 2hrs | Completed | 2022-10-07 | 1.75hrs
|  |  | Complete CRUD implementation for student management system | 2hrs | Completed | 2022-10-08 | 2hrs
|  |  | Practice Entity mapping | 3hrs | In Progress 40% | 2022-10-08 | 2.5hrs
|  |  | Learn about Cascade types | 1hr | Completed | 2022-10-08 | 45mins
|  |  | Explore Web Socket | 2hrs | Completed | 2022-10-09 | 4hrs
|  |  | Learn about Generation types | 1hr | Not Started | 2022-10-09
|  |  | Learn about Bean scopes | 1.5hrs | Not Started | 2022-10-09